## Status
MTRN4230 Asst 2 Requirements Tracking
Last updated | 20170824 |  | Group number |  |  | A
Updated by | Ken |  | L
Requirement number | Marks | Status | Date last tested | Responsible person | Tested by | Title | Description | Comments
GUI |  |  |  | (group member) | (group member)
1.1 | 2 | Pass. | 20170814 | Ken | Everyone | Startup checklist | Displays a startup checklist which prompts the user for confirmation where necessary and automatically updates as the Robot System is started up
1.2 | 3 | Pass. | 20170814 | Ravi | Everyone | Advise pose and I/O | Advise the user about the current robot pose and I/O status (pose of end effector and joint angles) even while the robot is in motion. This will require multitasking in RAPID
1.3 | 1 | Pass. | 20170814 | Ravi | Everyone | Advise commands | Advise the user about any commands sent to or from the Robot System in a user-readable format
1.4 | 1 | Fail. Solution unknown. | 20170814 | Ken |  | Advise comms lost | Advise the user when communication is lost due to an e-stop being triggered
1.5 | 1 | Pass. | 20170814 | Jay | Jay | Control I/O | Control the vacuum pump, vacuum solenoid, conveyor enable, conveyor direction
1.6 | 2 | Pass. | 20170814 | Jay | Jay | Display video | Display a live video feed from both cameras simultaneously
1.7 | 3 | Fail. Solution known. | 20170814 | Jay | Jay | Detect blocks | Display the status (pose, colour, shape, upper_surface, reachable etc.) of all visible Qwirkle blocks overlaid on the table video feed
1.8 | 2 | Fail. Solution known. | 20170814 | Jay | Jay | Detect boxes | Display the positions and orientations of any (Lindt) boxes on the conveyor belt overlaid on the conveyor video feed
Error Handling
2.1 | 1 | Fail. Solution unknown. | 20170814 | Ken |  | Socket errors | All possible socket errors must be handled gracefully - without requiring restarting the GUI
2.2 | 1 | Pass. | 20170814 | Daniel | Everyone | Conveyor restart | Set ConRun to 0 if ConStat is set to 0 and gracefully handle restarting of the conveyor
RobotStudio
3.1 | 1 | Fail. Solution unknown. | 20170814 | Ken |  | Define frames | Define and display relevant coordinate frames - world frame, base frame, end effector frame, camera frames, table frame, conveyor frame
3.2 | 2 | Pass. | 20170814 | Herman | Herman | CAD model | Display a recognisable CAD model of the Robot Cell and surrounding area, accurately coloured and textured
3.3 | 2 | Pass. | 20170814 | Daniel | Daniel | Virtual controller | Move in simulation according to 4. Motion Control through the GUI when not connected to the real Robot System
Motion Control
4.1 | 2 | Pass. | 20170814 | Daniel | Daniel | Manual jogging | Manually jog each axis and each joint independently on robot using the keyboard or mouse or external controller (XBox/Playstation/byo)
4.2 | 5 | Pass. | 20170814 | Daniel | Daniel | Click and go | By clicking a position on either video feed, move the vacuum gripper to 10mm above the table or conveyor, with the end effector facing directly down at the requested position (as if preparing to pick up or drop off a chocolate). The absolute horizontal accuracy of the vacuum gripper must be within 5mm for full marks
4.3 | 0 | Pass. | 20170814 | Daniel | Everyone | Set pose | Move the robot to a specified final pose in either table frame or conveyor frame automatically (ignoring the possibility of collision)
4.3.1 | 1 | Pass. | 20170814 | Daniel | Daniel | Select motion mode | Ability to move in either linear or joint motion modes
4.3.2 | 1 | Pass. | 20170814 | Daniel | Daniel | Select speed | Ability to move at different speeds
4.3.3 | 1 | Fail. Solution unknown. | 20170814 | Ken |  | Identify reachability | Robot should advise user if target point is not reachable
4.4 | 2 | Fail. Solution unknown. | 20170814 | Ken |  | GUI control | Allow any motion to be paused and/or restarted from the input controller and indicate the pause/run status in the GUI. This will require multitasking in RAPID
Documentation
5.1 | 3 | Fail. Solution known. | 20170814 | Everyone | Emtiazul | Documentation | All of your functions must be well documented within the code in both Matlab and RAPID. Include at least a Help command, purpose / description, inputs, outputs, author, date last modified
5.2 | 1 | Pass. | 20170814 | Everyone | Everyone | Comms protocol | Your communication protocol must be clearly and explicitly defined in one of your relevant functions in both Matlab and RAPID
Project Management
6.1 | 2 | Pass. | 20170814 | Ken | Ken | Requirements tracking | An electronic copy of this requirements tracking spreadsheet should be submitted to your demonstrator in your lab time each week until your demonstration
6.2 | 2 | Fail. Solution known. | 20170814 | Everyone | Emtiazul | Code management | The current status of your code management practices will be queried by your demonstrator each week. You need to provide evidence that all group members are securely and reliably managing versions of your code, both for Matlab and RAPID. The easiest way to demonstrate this is through an online repository such as GitHub
6.3 | 3 | Fail. Solution known. | 20170814 | Everyone | Emtiazul | Management report | You will need to provide a short report (<5 pages) detailing your project management practices and giving evidence of group members’ relative contributions to asst 2 based on requirements tracking and changelogs. This report should be uploaded with your code
Total | 45

## Working
Status
Fail. Solution unknown.
Fail. Solution known.
Pass.